## Project schedule (hidden)
| Sysmtem Development Plan | [5 empty] | Project start: |  |  |  |  | 2025-01-27
| Lost and Found Managament System | [5 empty] | Display week: |  |  |  |  | 1
By: Mark Hiolin and Joben Baigtu
[7 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-01-27 to 2025-03-23
 | time axis 2025-01-27 to 2025-03-23
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning Phase
| Gantt Chart | Joben Baigtu | 100% | 2025-01-27 | 2025-01-28 | 2
| Project Overview | Mark Hiolin | 100% | 2025-01-28 | 2025-01-30
| Objective | Mark Hiolin | 100% | 2025-01-30 | 2025-02-01 | 3
| Scope | Mark Hiolin | 80% | 2025-02-01 | 2025-02-03 | 3
| Constraint | Mark Hiolin | 70% | 2025-02-03 | 2025-02-05 | 3
| Risk | Mark Hiolin | 50% | 2025-02-05 | 2025-02-08
System Analysis & Design
| Functional Requirement | Mark Hiolin | 0% | 2025-02-08 | 2025-02-09 | 2
| Non Functional Requirement | Mark Hiolin | 0% | 2025-02-09 | 2025-02-10
| System Architecture | Mark Hiolin | 10% | 2025-02-08 | 2025-02-12
| Database Design | Mark Hiolin | 30% | 2025-02-09 | 2025-02-13 | 5
| Data Flow Diagram | Joben Baigtu | 20% | 2025-02-13 | 2025-02-16 | 4
| Interface Design | Joben Baigtu | 30% | 2025-02-16 | 2025-02-20 | 5
| Admin Panel Design | Mark Hiolin | 20% | 2025-02-20 | 2025-02-24
System Development
| Front End Development | Mark Hiolin | 30% | 2025-02-28 | 2025-03-10 | 11
| Back End Development | Mark Hiolin | 60% | 2025-03-10 | 2025-03-19 | 10
| Image Upload/ Storage | Mark Hiolin | 20% | 2025-03-19 | 2025-03-23 | 5
| Push Notification | Mark Hiolin | 0% | 2025-03-23 | 2025-03-27 | 5
Sytem Testing/ Implementation
| Unit Testing | Joben Baigtu | 0% | 2025-03-27 | 2025-03-31 | 5
| Integration | Joben Baigtu | 0% | 2025-03-31 | 2025-04-04 | 5
| System Testing | Joben Baigtu | 0% | 2025-04-04 | 2025-04-08 | 5
| User Acceptance Testing | Joben Baigtu | 0% | 2025-04-08 | 2025-04-13 | 6
Insert new rows ABOVE this one

## Project schedules
| Sysmtem Development Plan | [5 empty] | Project start: |  |  |  |  | 2025-01-27
| Lost and Found Managament System | [5 empty] | Display week: |  |  |  |  | 8 | [27 empty] | Project Percent Completion: | [9 empty] | 88.93%
By: Mark Hiolin and Joben Baigtu
[7 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-03-17 to 2025-05-11
 | time axis 2025-03-17 to 2025-05-11
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning Phase
| Gantt Chart | Joben Baigtu | 100% | 2025-01-27 | 2025-01-28 | 2
| Project Overview | Mark Hiolin | 100% | 2025-01-28 | 2025-01-30
| Objective | Mark Hiolin | 100% | 2025-01-30 | 2025-01-31 | 2
| Scope | Mark Hiolin | 100% | 2025-01-31 | 2025-02-01 | 2
| Assumptions | Mark Hiolin | 100% | 2025-02-01 | 2025-02-02
| Constraint | Mark Hiolin | 100% | 2025-02-02 | 2025-02-03 | 2
| Risk | Mark Hiolin | 100% | 2025-02-03 | 2025-02-04
System Analysis & Design
| Gather and Analyze Requirement | Mark Hiolin | 100% | 2025-02-04 | 2025-02-11 | 8
| Functional Requirement | Mark Hiolin | 100% | 2025-02-11 | 2025-02-13
| Non Functional Requirement | Mark Hiolin | 100% | 2025-02-13 | 2025-02-15
| Database Design | Mark Hiolin | 100% | 2025-02-15 | 2025-02-17 | 3
| Data Flow Diagram | Joben Baigtu | 100% | 2025-02-17 | 2025-02-19 | 3
| Interface Design | Joben Baigtu | 100% | 2025-02-19 | 2025-02-22 | 4
| Admin Panel Design | Mark Hiolin | 100% | 2025-02-22 | 2025-02-25
System Development
| Sprint 1: User Management and Authentication | Joben Baigtu | 100% | 2025-02-25 | 2025-03-04 | 8
| Sprint 2: Lost and Found Submission | Mark Hiolin | 100% | 2025-03-04 | 2025-03-11 | 8
| Sprint 3: Claiming & Verification Process | Mark Hiolin | 100% | 2025-03-11 | 2025-03-18 | 8
| Sprint 4: User Report | Mark Hiolin | 100% | 2025-03-18 | 2025-03-25 | 8
Sytem Testing/ Implementation
| Unit Testing | Joben Baigtu | 100% | 2025-03-25 | 2025-03-29 | 5
| Conduct Integration | Joben Baigtu | 100% | 2025-03-29 | 2025-04-02 | 5
| System Testing | Joben Baigtu | 80% | 2025-04-02 | 2025-04-07 | 6
| User Acceptance Testing | Joben Baigtu | 70% | 2025-04-07 | 2025-04-15 | 9
Deploy/Review/ Launch
| Finalize Documentation | Mark Hiolin | 80% | 2025-04-15 | 2025-04-19
| Deploy App (Private and Public Release) | Joben Baigtu | 30% | 2025-04-19 | 2025-04-22
| Monitor Usage and Performance | Joben Baigtu | 80% | 2025-04-22 | 2025-04-25
| Collect User Feedback | Joben Baigtu | 70% | 2025-04-25 | 2025-04-28
| Implement Minor Enhancement | Mark Hiolin | 80% | 2025-04-28 | 2025-05-02
| Officially Launch the app for public use | Joben Baigtu | 0% | 2025-05-02 | 2025-05-03
|  | Completion | 88.93%